## Sheet1
Creating the API Tasks |  |  | Hours Required | Hours Actual
X | Research (testing and documentation) |  | 2 | 0.5
Setup Dev / test environment
X |  | Setup server to host replicated test SQL database | 6 | 2
X |  | Setup replicated SQL database | 6 | 2
Authentication to Fluent servers
X |  | Create API keys | 1 | 0.25
X |  | Create working authentication calls | 2 | 2
Mapping the data set from API to SQL (The data from vendor shouldn’t have changed)
+ |  | Create API calls to retreive the data | 12
+ |  | Analyze the data from API call compared to test SQL DB | 2
|  | Create SQL write methods to write to test DB | 12
Configure automation and Interval of automation
|  | Add to scheduler | 2
|  | Create a throttling method | 10
Verify Data integrity
|  | compare reports between Live SQL and Test SQL | 15
|  | Hytec Approval | 4
Configure on live system
|  | Remove Vsend processes (may require Fluent) | 2
|  | implent new API program to Hytec Server | 10
|  |  | Total Hours | Total Actual
|  |  | 86 | 6.75